Dated                                   2017

THE GOVERNMENT OF THE REPUBLIC OF armenia

acting on behalf of the republic of armenia

(AS THE GOVERNMENT)	(1)

and

armpower CJSC (as THE developer)	(2)

and

| RENCO S.p.A (AS THE SPONSOR) | (3) |
| --- | --- |

FRAMEWORK AGREEMENT to Design, Develop, Finance, Construct, Own, Operate and Maintain a 250MW Gas-Fired Combined Cycle Power Plant at Yerevan, Armenia

CONTENTS

Article	Heading	Page

1	DEFINITIONS AND INTERPRETATION	2

2	SCOPE OF AGREEMENT AND TERM	26

3	project structure	28

4	Extension of Milestone Dates	32

5	SITE	33

6	Engineering Procurement and Construction of the Plant	35

7	StarT-UP, COmmissioning & COmmercial Operation	38

8	Gas AND UTILITY SUPPLY	42

9	PAYMENT STATEMENTS AND INVOICING	45

10	SALE AND PURCHASE OF ELECTRICITY AND CONTRACTED CAPACITY	47

11	foreign exchange	50

12	Government Support	51

13	Indemnification and liability	55

14	FORCE MAJEURE AND ADVERSE CONDITIONS	57

15	change in law	63

16	Events of Default	65

17	Termination	67

18	DISPUTE RESOLUTION	70

19	REPRESENTATIONS AND WARRANTIES	74

20	MISCELLANEOUS PROVISIONs	77

APPENDIX 1	Project Site	85

APPENDIX 2	Conditions Precedent	86

APPENDIX 4 	Compensation on Termination	88

APPENDIX 5	Project Schedule	90

APPENDIX 6	Tariff Schedule	91

APPENDIX 10	Preliminary Land Agreement	92

APPENDIX 12	Terms of Reference	93

APPENDIX 13	YTPP Letter No. 704	95

THE AGREEMENT is made at				on this the	day of		2017

BETWEEN:

THE GOVERNMENT OF THE REPUBLIC OF ARMENIA, ACTING ON BEHALF OF THE REPUBLIC OF ARMENIA having its administrative office at Republic Square, Government House 1, 0010 Yerevan, Republic of Armenia, hereinafter referred to as the "Government" (which expression shall, unless the context requires otherwise, include its successors and permitted assigns); and

ARMPOWER CJSC, a company incorporated and registered in the Republic of Armenia pursuant to Armenian law (with company number 286·120·924562), and having its registered office at Vazgen Sargsyan Street 10, Kentron, 0010 Yerevan, Armenia, hereinafter referred to as the "Developer" (which expression shall, unless the context requires otherwise, include its successors and permitted assigns); and

RENCO S.p.A, a public company incorporated and registered in Italy pursuant to Italian law (with company number 13250670158) and being legally based at Viale Venezia 53, 61121 – Pesaro, Italy, hereinafter referred to as the "Sponsor" (which expression shall, unless the context requires otherwise, include its successors and permitted assigns).

WHEREAS:

The Government intends to engage a private developer to develop the Project at a site near Yerevan city, Armenia.

The Government has entered into a Memorandum of Understanding with the Sponsor detailing the indicative commitments and responsibilities of the Government and the Sponsor in relation to the Project.

The Developer has been incorporated by the Sponsor for the purposes of implementing the Project.

This Agreement sets forth the terms and conditions of the implementation and structure of the Project, and supersedes the Memorandum of Understanding.

NOW, IT IS AGREED AS FOLLOWS:

ARTICLE 1

# DEFINITIONS AND INTERPRETATION

## Interpretations

In the Agreement unless the context otherwise requires:

### any reference to a statutory provision shall include such provision as it is from time to time modified or re-enacted or consolidated so far as such modification or re-enactment or consolidation applies or is capable of applying to any transactions entered into hereunder;

### the words importing singular shall include plural and vice versa, and words denoting natural persons shall include partnerships, firms, companies, corporations, joint ventures, trusts, associations, organisations or other entities (whether or not having a separate legal entity);

### the table of contents and any headings in the Agreement are for ease of reference only and shall not affect the construction or interpretation of the Agreement;

### the words "include" and "including" are to be construed without limitation;

### any reference to any period of time shall mean a reference to that according to Yerevan time;

### "Article" and "Appendix" shall refer, except where the context otherwise requires, to Articles of and any Appendix to the Agreement.  The Appendices to the Agreement shall form an integral part and parcel of the Agreement and will be in full force and effect as though they were expressly set out in the body of the Agreement;

### any reference at any time to any agreement, deed, instrument, licence or document of any description shall be construed as reference to that agreement, deed, instrument, licence or other document as amended, varied, supplemented, modified or novated at the time of such reference;

### unless otherwise stated, any reference to any period commencing "from" a specified day or date and "till" or "until" a specified day or date shall include both such days or dates;

### unless otherwise specified, any interest to be calculated and payable under the Agreement will apply on a 365 Day basis and shall accrue from Day to Day from the respective due date until the relevant payment obligation is fulfilled; and

### references to any gender include all genders.

## Ambiguities and Discrepancies

In case of ambiguities or discrepancies within the Agreement, the following shall apply:

### between two Articles of the Agreement, the provisions of specific Articles relevant to the issue under consideration shall prevail over those in other Articles;

### between any value written in numerals and that in words, the latter shall prevail; and

### between the provisions of the Agreement and any other documents forming part of the Agreement, the former shall prevail.

## Definitions

In the Agreement, unless the context otherwise requires, the following terms shall have the following meanings assigned/ascribed thereto:

| Abandonment | - the voluntary cessation of construction or operation of the Plant or the withdrawal of all, or substantially all, personnel by the Developer from the Project Site cumulatively for more than one hundred and eighty (180) Days in a calendar year for reasons other than a Force Majeure or Adverse Condition Event; |
| --- | --- |
| Acceptance Act | a certificate issued by the Acceptance Commission confirming that the Plant has been completed in accordance with the documents set out in Article 6.1(b)(i)-6.1(b)(vi) and has passed the Commissioning Tests; |
| Acceptance Commission | - the temporary acceptance commission formed by the Government in accordance with all Applicable Laws for the purpose of determining the Commissioning Tests and conducting the Plant acceptance activities; |
| Additional Equity Partner | - has the meaning given to it in Article 3.3(c); |
| Additional Partner Notice | - has the meaning given to it in Article 3.3(c); |
| Additional Technology Partner | - has the meaning given to it in Article 3.3(c); |
| Adverse Condition Event | - has the meaning given to it in Article 14.1(b); |
| Affiliate | any Person who Controls or is Controlled by (directly or indirectly) another Person, including where a Person is a company, the ultimate holding company of such Person, any holding company of such Person and any subsidiary (direct or indirect) of such holding company; |
| Agreement | this agreement, including any Appendices, and as the same may be amended from time to time in accordance with its provisions; |
| Ambient Conditions | means together ambient air temperature, ambient relative air humidity at the Project Site and the altitude of the Project Site; |
| AMD or Dram | means the lawful currency of Armenia; |
| Applicable Laws | all laws in force and effect as of the Signing Date and which may be promulgated or brought into force and effect hereinafter in Armenia, including statutes, rules, regulations, directions, bye-laws, notifications, ordinances and judgments having force of law, or any final interpretation by a court of law having jurisdiction over the matter in question, as may be in force and effect during the subsistence of the Agreement; |
| Applicable Permits | any and all permissions, consents, clearances, licences, authorisations, consents, no-objections, approvals and exemptions under or pursuant to any of the Applicable Laws or from any Government Authority required in connection with the Project and for undertaking, performing or discharging the obligations contemplated by the Agreement or any Project Agreement; |
| Armenia | the Republic of Armenia; |
| Armenia Revenue Authority | the State Revenue Committee of the Government of the Republic of Armenia, or any relevant successor thereof; |
| Assigned Amount | has the meaning given to it in Article 10.1(c); |
| Calculation Date | the Day on which a Purchase Price is calculated, such Day being the termination date specified in a Termination Notice issued in accordance with Article 17.4; |
| Change in Law | means the adoption, coming into effect, modification, reinterpretation, cancellation, withdrawal or suspension, after the Signing Date by the Government or any Government Authority of any Applicable Law, Tax or Applicable Permit, if, in the latter case, not due to the Developer’s fault; |
| COD Deadline | the date that is 90 Days after the Scheduled Commercial Operation Date; |
| COD Longstop Date | the date that is 180 Days after the Scheduled Commercial Operation Date; |
| Commercial Operation Date | the date on which PSRC adopts a resolution for the License Revision and approval of the Tariff; |
| Commissioning Plan | has the meaning given to it in Article 6.3; |
| Commissioning Tests | a series of pre-commissioning and commissioning tests determined by the Acceptance Commission in accordance with the Commissioning Plan and Applicable Laws, including at a minimum the Dispatchable Capacity Test, pursuant to which the Developer will demonstrate that the Plant has been constructed in accordance with Article 6.1, meets the requirements of all Applicable Laws and the Plant's technical specifications and is capable of commercial operation in accordance with the same and the terms of this Agreement; |
| Committed Equity | means the amount of Equity funded on the Calculation Date; |
| Committed Offtake Term | a period commencing on the Commercial Operation Date and expiring on the twentieth (20th) anniversary of the Commercial Operation Date; |
| Completion Act | a document issued by the Yerevan Municipality based on the Acceptance Act, certifying that the construction of the Plant has been completed and the Plant is ready for commercial operation in accordance with Applicable Laws; |
| Conditions Precedent | those conditions precedent to the effectiveness of this Parties’ rights and obligations under this Agreement set out at Appendix 2; |
| Conditions Precedent Deadline | the date that is 180 Days after the Signing Date, subject to any extension in accordance with the terms of this Agreement; |
| Construction Start Date | the date that is 30 Days after the EPC Signature Date;, subject to receiving by the Developer of the License; |
| Contracted Capacity | means the nominal power capacity of the Plant (in MW), as set out in the License, less the nominal power capacity unavailable due to equipment maintenance in the relevant period, as determined in accordance with the Applicable Laws, such capacity to be used for the purposes of calculating the amounts payable by the Offtaker to the Developer under the Power Purchase Agreement for making the Dispatchable Capacity available by the Plant and for other purposes specified in this Agreement; |
| Control | - means the power, directly or indirectly, to direct or cause the direction of the management and policies of a Person, whether through the ownership of voting securities or any interest carrying voting rights, or to appoint or remove or cause the appointment or removal of any directors (or equivalent officials) or those of its directors (or equivalent officials) holding the majority of the voting rights on its board of directors (or equivalent body), whether by contract or otherwise, and "Controlled" shall be construed accordingly; |
| Cost | - with respect to any Change in Law, any cost or expense reasonably and properly incurred and documented relating to the Project directly resulting from, or otherwise directly attributable to, such Change in Law, that is incurred or suffered by the Developer, and not otherwise covered by the receipt of insurance proceeds, which costs or expenses may include: - capital costs; - financing costs; - costs of operation and maintenance; - costs of Taxes imposed on or payable by the Developer; or - reduction in the revenue received by the Developer; |
| Day | the 24 (twenty four) hour period beginning and ending at 00:00 Yerevan time; |
| Deemed Period | has the meaning given to it in Article 10.2; |
| Delivery Point | has the meaning given to it Article 5.2; |
| Developer Event of Default | has the meaning given to it in Article 16.1; |
| Developer Event of Default Purchase Price | the purchase price set out in Appendix 3; |
| Dispatchable Capacity | means the net power capacity (in MW) that the Plant shall be capable of dispatching upon request of the System Operator and/or the Offtaker, as applicable, being the Contracted Capacity adjusted in accordance with Applicable Laws to take into account (i) the Ambient Conditions, and (ii) degradation due to ageing during the Term, and as shown by the most recent Dispatchable Capacity Test or assessed by an Independent Engineer, as applicable; |
| Dispatchable Capacity Test | means the test to establish the Dispatchable Capacity carried out firstly as the Commissioning Tests and then as required in accordance with Applicable Laws; |
| Effective Date | the date on which the Developer issues notice to the Government that each of the Conditions Precedent have been satisfied by the Party responsible for satisfying it or waived by the Party not responsible for satisfying it; |
| EPC Contract | the engineering, procurement and construction contract entered into by the Developer and the EPC Contractor in relation to the Project; |
| EPC Contractor | a Permitted Technology Partner that will design, engineer, construct, commission and complete the Plant, appointed in accordance with Article 3.3(a); |
| EPC Signature Date | the date on which the EPC Contract has been signed; |
| Equity | means the capital of the Developer attributable to its shareholders in respect of the investment in the Developer by its shareholders, whether as subscription for shares or as shareholder loans; |
| Exemplary Documents | means the exemplary forms of each of the Power Purchase Agreement, the Gas Supply Agreement, the Power Supply Agreement, the Water Supply Agreement and the Commissioning Electricity Purchase Agreement, as approved by the Government or PSRC, which shall be signed as a matter of the Applicable Laws by the relevant counterparts upon the relevant requirements set out in the Applicable Laws being satisfied; |
| Expert Commission | the temporary expert commission formed by the Government in accordance with all Applicable Laws for the purpose of expert examination and approval of the Plant design documentation and the environmental impact assessment report for the Project submitted by the Developer; |
| Financial Close | the date which the Financing Documents have become effective and the Developer has access to financing; |
| Financial Close Deadline | the date that is 180 Days after the Signing Date; |
| Financial Close Longstop Date | the date that is 90 Days after the Financial Close Deadline; |
| Financing Documents | any and all loan agreements, bonds, indentures, security agreements, note or bond purchase agreements, interest rate, hedging arrangements, and other collateral and related documents which may be entered into by the Developer with respect to the financing and any refinancing of the Project, other than shareholder loans or other shareholder financing documents; |
| Financing Parties | any Person or Persons providing financing or refinancing to the Developer under the Financing Documents, and its or their permitted successors and assigns, including any agent or trustee for such Person or Persons; |
| Force Majeure Event | has the meaning given to it in Article 14.1; |
| Force Majeure or Adverse Condition Event | has the meaning given to it in Article 14.1; |
| Gas | gas of a quality that at a minimum meets the GOST 5542-2014 "Natural fuel gases for industrial and domestic use" standard; |
| Gas Delivery Point | the Interface point for the Gas supply to the Project Site, as specified in the GSA, as determined in accordance with the ToR; |
| Gas Supplier | means GazProm Armenia CJSC or its successors; |
| Gas Supplier Facilities | means the gas pipeline, and associated facilities developed, built, owned, operated and maintained by the Gas Supplier for delivery of Gas to the Gas Delivery Point; |
| Gas Supply Agreement or GSA | means a gas supply agreement between the Developer and the Gas Supplier in the form of the relevant Exemplary Document to deliver the Gas required for the Project to the Gas Delivery Point, at specified times, price, quality and quantity, for the duration of the Term; |
| Gas Supply Force Majeure | means any Utility Supply Force Majeure constituting any disruption in the delivery to the Gas Delivery Point of Gas needed to test, commission or operate the Plant at its Dispatchable Capacity, but only if and to the extent that: - such disruption is not caused by a Force Majeure Event; and - such disruption exceeds on a cumulative basis three (3) Days in any given calendar month and/or twelve (12) Days in any calendar year. |
| Good Industry Practice | those practices, methods and acts as are in accordance with good standards of prudence applicable to the international electricity generation industry which would have been expected to accomplish the desired result at the lowest reasonable cost consistent with reliability, safety and expedition; |
| Government Authority | the Government of the Republic of Armenia, the National Assembly, or any governmental department, commission, board, body, bureau, agency, authority, instrumentality, administrative body of Armenia, at central, or local level, having jurisdiction over the Developer, the Project Site, or the Plant or any portion thereof, or the matter in question. For the avoidance of doubt this provision does not apply to the judiciary; |
| Government Confirmation | a written confirmation from the Government of the Republic of Armenia, and/or the Ministry of Finance of the Republic of Armenia and/or the Ministry of Justice of the Republic of Armenia, as applicable, in respect of the Project confirming that: - the Government of the Republic of Armenia may enter into this Agreement on behalf of the Republic of Armenia; - the Government has received all required authorisation in relation to the Agreement and the Government's entry into it as are necessary so as to ensure the Agreement has full force and effect; and - all obligations and liabilities of the Government pursuant to this Agreement are valid and binding and fully enforceable and not subject to any further regulation, authorisation, budgetary approval or restriction or issuance of a separate budgetary guarantee. |
| Government Event of Default | has the meaning given to it in Article 16.2; |
| Government Event of Default Purchase Price | the purchase price set out in Appendix 3; |
| Independent Engineer | a consulting engineer, independent from the interests of the EPC Contractor and the Developer, approved by the Government and employed or engaged jointly, from time to time, by the Developer and the EPC Contractor in accordance with an independent engineer appointment agreement to be agreed between the Parties, for the design review, approval and supervision of the construction, testing, commissioning and acceptance of the Plant, and determination of various matters, all in accordance with the provisions of this Agreement taking into account the requirements of the Applicable Laws ; |
| Independent Expert | means the expert appointed pursuant to Article 18.2(c) |
| Insolvency Event | - means: - in relation to the Developer, the: - passing of a resolution by the shareholders of the Developer for the winding up of the Developer; - voluntary filing by the Developer of a petition of bankruptcy, anticipated bankruptcy, liquidation, rehabilitation, moratorium or other similar relief; - appointment of a liquidator, temporary administrator, bankruptcy administrator or other similar officer in respect of the Developer in any proceeding in relation to the Developer, which appointment has not been set aside or stayed within sixty (60) Days of such appointment; or - the making by a court with jurisdiction over the Developer of a judicial act the Developer which is not stayed or is reversed by a court of competent authority within thirty (30) Days; and - in relation to the Government, the declaration by the Government of a moratorium on payments to its creditors or sovereign default (or any other declaration having the same effect), or an express admission by the Government that it no longer able to meet its payment obligations pursuant to this Agreement; |
| Interface | each construction connection and/or physical tie-in, between the Plant and the interconnection or delivery infrastructure of a counterparty to a Project Agreement, as applicable, including the Gas Delivery Point and the Delivery Point, and, where the location of such an interface is not specified in this Agreement, as specified in the relevant Project Agreement; |
| Land Acquisition Agreement | means the main land transfer agreement to be signed pursuant to the Preliminary Land Agreement under which ownership of the Project Site shall be transferred by the Owner to the Developer for the Project Site Price; |
| Late Payment Rate | a rate of interest per annum on the date of determination equal to the accounting rate of bank interest set out by the Central Bank of the Republic of Armenia for AMD, but not less than two per cent (2%) above the Dollar rate quoted for six (6) month London Interbank Offered Rates (LIBOR) under the caption “Money Rates” in The Wall Street Journal (or, if no such rate appears, the arithmetic mean of the offered quotations that appear on the relevant page (if any) on the Reuters Monitor Money Rates Service (or such other service as may replace the Reuters Monitor Money Rates Service for the purpose of displaying LIBOR)) on the due date or required date of payment in question, which rate shall be adjusted every six (6) months thereafter, provided that such rate does not exceed the maximum rate of interest permitted by Applicable Laws; |
| Licence | - means the licence to be obtained by the Developer from PSRC in accordance with Applicable Laws for the construction of the Plant and production of electrical energy (capacity); |
| License Revision | - means the revision of the License by PSRC to reflect that the Plant may enter into the production phase. |
| Loss | any real loss, damage, liability, payment and/or obligation (including those related to reasonable legal fees, and, for the avoidance of doubt, excluding any loss of income, loss of opportunity, indirect or consequential loss, damage, liability, payment or obligation); |
| Milestone Dates | the: Conditions Precedent Deadline; Financial Close Deadline; Construction Start Date; and Scheduled Commercial Operation Date; and any other date described as a Milestone Date in the Project Schedule. |
| MOU or Memorandum of Understanding | means the memorandum of understanding dated 2 December 2015 made between: the Government (represented by Minister Yervand Zakharyan); and the Sponsor (represented by Aslan Dyshekov), - detailing the indicative commitments and responsibilities of the Government, the Sponsor and subsequently the Developer (as an Affiliate of the Sponsor) in respect of the Project; |
| Net Electrical Energy | the sum of net electrical energy delivered by the Developer to the Offtaker at the Delivery Point; |
| O&M Contractor | - a Permitted Technology Partner that will provide services for the operation, maintenance and/or repair of the Plant; |
| Offtaker | Electric Networks of Armenia CJSC or its successors; |
| Owner | Yerevan TPP CJSC; |
| Partner Information | for a Person, excluding individuals, documentation or other evidence confirming: - registered office address; - principal place of business; - shareholding structure; - ultimate beneficial owners; and - key management structure; or for an individual: - the full name of such individual and, if applicable, the spouse; - citizenship(s) of such individual and, if applicable, the spouse; - permanent residential address of such individual and, if applicable, the spouse; and - if such individual is acting to in the interest of another individual or entity, information about such individual or entity listed herein; |
| Party | either the Government or the Developer as the context may require or admit and "Parties" means both the Government and the Developer; |
| Permitted Equity Partner | any Additional Equity Partner approved by the Government in accordance with Articles 3.3(b) and 3.3(c); |
| Permitted Technology Partner | any Additional Technology Partner approved by the Government in accordance with Articles 3.3(b) and 3.3(c); |
| Person | any individual, company, corporation, partnership, joint venture, trust, unincorporated organisation, government or governmental authority or agency or any other legal entity; |
| Plant | means a gas-fired, combined cycle, power plant with approximately 250MW average annual gross electrical energy generation capacity and with not less than 50.5% gross efficiency designed and constructed in accordance with the Plant's technical specification; |
| Plant Design Documentation | the Plant design documentation approved by the Expert Commission; |
| Power Purchase Agreement or PPA | means a power purchase agreement in the form of the relevant Exemplary Document relating to the sale by the Developer and purchase by the Offtaker of the Net Electrical Energy and the Contracted Capacity of the Plant; |
| Power Supply Agreement or PSA | a power supply agreement in respect of the Project to be entered into between the Developer and the Offtaker in the form of the relevant Exemplary Document pursuant to which initial energisation, backfeed and other electricity will be provided to the Developer as required for throughout the Term; |
| Preliminary Land Agreement | the preliminary agreement that has been entered into between the Owner and the Developer relating to the sale of the Project Site to the Developer (a copy of which is set out in Appendix 6); |
| Project | the project to design, develop, finance, construct, own, operate, and maintain the Plant at the Project Site; |
| Project Agreements | means the Power Purchase Agreement, the Gas Supply Agreement, the Power Supply Agreement, the Water Supply Agreement and any document referred to in Article 1.1(a)(i); |
| Project Schedule | the Project implementation schedule, as set out in Appendix 4; |
| Project Site | the land adjacent to the existing thermal power plant of Yerevan TPP CJSC, more specifically described on the site plan attached at Appendix 1; |
| Project Site Price | the price of the Project Site, as set out in the Preliminary Land Agreement; |
| PSRC | means the Public Services Regulatory Commission of the Republic of Armenia; |
| Purchase Price | means the Government Event of Default Purchase Price and the Developer Event of Default Purchase Price; |
| Saving | - with respect to any Change in Law, any savings or reduction of cost or expense relating to the Project resulting from, or otherwise attributable to, such Change in Law, that is realised by the Developer, which costs or expenses may include: capital costs; financing costs; costs of operation and maintenance; costs of Taxes imposed on or payable by the Developer; or increase in revenue of the Developer; |
| Scheduled Commercial Operation Date | - the date that is 750 Days from the EPC Signature Date; |
| Senior Debt | means all amounts required to be paid or repaid by the Developer pursuant to the Financing Documents; |
| Signing Date | the date the Agreement is concluded pursuant to Article 20.13; |
| Systems Operator | has the same meaning as "electrical energy system operator" as defined in the Law on Energy of the Republic of Armenia; |
| Tariffs | the payment tariffs determined from time to time by PSRC in accordance with the Tariff Schedule, at which the Offtaker will purchase the Net Electrical Energy and the Contracted Capacity of the Plant under the Power Purchase Agreement; |
| Tariff Schedule | the agreed tariff schedule set out at Appendix 5; |
| Taxes | any Armenian taxes including taxes on corporate income, excise duties, customs duties, value added tax, sales tax, local taxes, and any impost or surcharge of like nature on the goods, materials, equipment and services incorporated in and forming part of the Project, levied or imposed by any Government Authority, but excluding any interest, penalties and other sums in relation thereto imposed on any account whatsoever; |
| Technology Partner | - an EPC Contractor or a O&M Contractor, or any other technology partner intended to be contracted by the Developer for the purposes of the Project; |
| Term | the term of the Agreement as set out at Article 2.3; |
| Third Party Claim | has the meaning given to it in Article 13.4; |
| ToR | means the terms of reference attached at Appendix 7; |
| Transmission Code | means the: Law on Energy of the Republic of Armenia; regulation on interrelations between the entity holding the license of electrical energy system operator and other licensed entitles of the electrical energy system adopted by PSRC resolution #347-N dated 02/07/2008; regulation on operational relations between the entity holding electrical energy distribution license and the entities holding electrical energy production and transmission licenses adopted by PSRC resolution #348-N dated 02/07/2008; other Applicable Laws setting out technical and operational requirements related to constructing, testing, commissioning and operation of power plants and their relations with other licensed entities of the energy system of the Republic of Armenia; and any subsequent Applicable Law which replaces any of the above; |
| Transmission System | shall have the equivalent meaning of "transfer (transmission) network" as defined in the Law on Energy of the Republic of Armenia; |
| USD or Dollar | means the lawful currency of the United States of America; |
| Utility Supply Force Majeure | means any disruption, in the supply of Gas, water, power or any other utility or service provided by an entity licensed or regulated by the PSRC needed to test, commission or operate the Plant at its Dispatchable Capacity, but only if and to the extent that: - such disruption, despite the exercise of reasonable diligence and the observance of Good Industry Practice by the Developer, cannot be or be caused to be prevented, avoided or removed by the Developer; - such disruption materially adversely affects the ability of the Developer to test, commission or operate the Plant in accordance with Applicable Laws and Good Industry Practice, and the Developer has taken all reasonable precautions, due care and reasonable measures in order to avoid the effect of such disruption on the Developer's ability to so test, commission or operate the Plant; - such disruption is not the direct or indirect result of the failure of the Developer to perform any of its obligations under any of the Project Agreements, and - the Developer has given the Government prompt notice describing such disruption and its effect upon the ability of the Developer to test or, commission or operate the Plant;] |
| Water Supply Force Majeure | means any Utility Supply Force Majeure constituting any disruption in the delivery to the water delivery Interface of water needed to test, commission or operate the Plant at its Dispatchable Capacity, but only if and to the extent that: - such disruption is not caused by a Force Majeure Event; and - such disruption exceeds on a cumulative basis three (3) Days in any given calendar month and/or thirty six (36) Days in any calendar year; |
| Water Supply Agreement or WSA | means the water supply and sewage services agreement in respect of the Project to be entered into between the Developer and VEOLIA Djur CJSC (or its successors) in the form of the relevant Exemplary Document pursuant to which water, and sewage services, will be provided to the Developer throughout the Term. |

ARTICLE 2

# SCOPE OF AGREEMENT AND TERM

## Concession

In consideration of the Developer performing its obligations as set out in the Agreement, the Government hereby grants to the Developer for the duration of the Term the exclusive right to implement the Project on the Project Site and to own and use the Project Site for such purposes, including the right and obligation to:

### sell to the Offtaker in accordance with Applicable Law the Contracted Capacity and the Net Electrical Energy of the Plant, as well as sell any ancillary services or products that the Plant is capable of providing to any Person in accordance with Applicable Laws; and

### connect, remain connected to, and use and evacuate electricity to, the relevant electricity transmission network as is permitted by Applicable Laws in order for it to deliver electrical energy to the Delivery Point.

## Acceptance of the Concession

The Developer hereby accepts the concession and agrees to implement the Project in accordance with the provisions of this Agreement, any applicable Project Agreement, Good Industry Practice, all Applicable Laws and Applicable Permits.

## Term of Agreement

### The Term shall commence on the Signing Date and shall, unless extended or terminated earlier in accordance with the terms of the Agreement, expire at the end of the Committed Offtake Term.

### The Term and the Committed Offtake Term may be extended, subject to the Parties agreeing in writing the terms and conditions of any extension in advance of the date upon which the Term or Committed Offtake Term, as applicable, would otherwise expire.

### The term of operation of the Plant by the Developer shall not be limited to the Committed Offtake Term or the Term.

## Conditions Precedent to Effective Date

## The rights and obligations of the Parties under the Agreement are, unless the context requires otherwise, conditional upon the fulfilment of the Conditions Precedent.

### If any Conditions Precedent is not delivered on or before the Conditions Precedent Deadline,  then this Agreement may be terminated as provided in Article 17.1.

### Notwithstanding the above, all dates and deadlines set out in this Agreement shall be calculated from the Signing Date, unless the context requires otherwise.

## Sponsor Obligations

The Parties and the Sponsor agree and acknowledge that the Sponsor is a party to this Agreement solely for the purposes of ensuring that the obligations under Article 3.3 are complied with.

ARTICLE 3

# project structure

## Termination of the Memorandum of Understanding

### The Parties agree and acknowledge that the MOU shall automatically terminate on the Effective Date or upon termination of this Agreement, whichever comes first.

## Project Timeline

### Conditions Precedent

### Following the Signing Date:

#### the Government shall commence the procedure required to issue the Government Confirmation; and

#### each Party shall use all reasonable endeavours to deliver and satisfy those Conditions Precedent for which it is responsible, as set out in Appendix 2 on or before the Conditions Precedent Deadline.

### Financial Close and EPC Signature

### Following the Signing Date, the Developer shall use all reasonable endeavours to achieve Financial Close and the EPC Signature Date by the Financial Close Deadline, as each such date may be extended by the provisions of this Agreement.

### Project Agreements

#### In order to ensure the successful development and implementation of the Project, the Government shall use its best efforts to cause, at no financial cost to the Government, that the following agreements are entered into with the Developer by the relevant counterparty, and, if required by the Applicable Laws, approved by and/or registered with the competent Government Authority, without unreasonable delay:

##### the Land Acquisition Agreement;

##### the Project Agreements to be entered in the form of Exemplary Documents, upon satisfaction of the requirements envisaged by all Applicable Laws; and

##### any other agreement reasonably required by the Developer to be entered in relation to the Project with any state-owned, licensed or regulated entity in order for the Developer to develop and implement the Project and/or for the Government to give effect to the rights granted to the Developer under this Agreement.

#### The Developer acknowledges that under the Applicable Laws in effect as of the Signing Date, the Gas Supply Agreement, the Power Supply Agreement and the Water Supply Agreement can only be entered into after building the relevant interconnection infrastructure, and the Power Purchase Agreement can only be entered into after the License Revision.

#### The Parties agree and acknowledge that to the extent required by the Applicable Laws the Project Agreements shall substantially be in their template form, as approved by the relevant Government Authority but may be amended as agreed between the Developer, the relevant counterparty, and the PSRC or the Government, as applicable.

### Engineering, Procurement and Construction, and Commercial Operation of the Plant

### The Developer shall commence construction of the Plant on the Project Site by the Construction Start Date, and commercial operation by the Scheduled Commercial Operation Date, in accordance with and subject to, the provisions of Articles 6 and 7, and any other relevant provisions of this Agreement.

## Equity and Technological Partners

### The Parties and the Sponsor agree that, subject to the below, the EPC Contract shall be entered into either with:

#### a consortium of the Sponsor and a Permitted Technology Partner acting on a joint and several basis; or

#### the Sponsor, or an Affiliate of the Sponsor, who shall subcontract a Permitted Technology Partner for its services.

### The Government shall be notified of any intended share sale or allotment of shares in the Developer to any potential shareholder (an "Additional Equity Partner"), or intended participation in the Project of any Person in the capacity of a Technology Partner (an "Additional Technology Partner"), in writing together with the Partner Information (an "Additional Partner Notice").

### Without prejudice to any requirement of the Applicable Laws (including obtaining the permission of PSRC and/or the State Commission for Protection of Economic Competition of the Republic of Armenia, as applicable) within fifteen (15) Days of receiving a compliant Additional Partner Notice, the Government shall inform the Developer and the Sponsor in writing whether or not it consents to the participation of such Additional Equity Partner or Additional Technology Partner. Participation in the Project of an Additional Equity Partner or Additional Technology Partner, shall not be permitted without the consent of the Government, provided that such consent shall not be unreasonably delayed, and may be withheld by the Government if, and only if, in its reasonable opinion:

#### the participation of the Additional Equity Partner or Additional Technology Partner in the Project will be prejudicial to the national security of Armenia; or

#### the Additional Equity Partner or Additional Technology Partner is registered or organised in, or Controlled by any Person of a country with which Armenia does not have diplomatic relations; or

#### the participation of the Additional Equity Partner or Additional Technology Partner in the Project will create more onerous obligations, liabilities or risks for the Government than those imposed upon it pursuant to this Agreement.

#### Once approved in accordance with this Article, the relevant Additional Equity Partner or Additional Technology Partner, as applicable, shall become a Permitted Equity Partner or Permitted Technology Partner, as applicable.

### Should the Government fail to respond to the Developer and the Sponsor within fifteen (15) Days of a compliant Additional Partner Notice being received by the Government in accordance with Article 3.3(a) the Government's consent to the participation of the Additional Equity Partner or Additional Technology Partner in the Project will have deemed to have been granted.

### The Developer and the Sponsor shall procure that any Additional Equity Partner shall only become a Permitted Equity Partner on the condition that any such Additional Equity Partner agrees to be bound by the terms of this Agreement in its capacity as a shareholder in the Developer.

ARTICLE 4

# Extension of Milestone Dates

## If:

### a material breach of the terms of this Agreement by the Government; or

### a Force Majeure, a Change in Law or an Adverse Condition Event,

## directly delays the achievement of any Milestone Dates, or the achievement of the Commercial Operation Date, then each such Milestone Date, and/or the Scheduled Commercial Operation Date, as applicable shall be adjusted by the Parties to take into account the effect of such delay in the achievement of the relevant Milestone Date, or the Commercial Operation Date, provided that:

#### such dates shall not be extended to the extent that such delay would have nevertheless been experienced as a direct result of any fault of the Developer had such event not occurred; and

#### that the Developer shall have made all reasonable endeavours in accordance with Good Industry Practice to prevent or reduce to a minimum and mitigate the effect of any delay, including recourse to alternate sources of services, equipment and materials and construction equipment.

ARTICLE 5

# SITE

## Acquisition of the Project Site

### The Parties acknowledge that:

#### the design of the Plant, and the agreed boundaries of the Project Site, have been agreed with the Owner to make maximum use of the wider area of remaining land belonging to the Owner, which is adjacent to the Project Site; and

#### the Developer and the Owner have entered into the Preliminary Land Agreement with the Signing Date being a condition precedent to the Preliminary Land Agreement becoming binding on the Developer.

### The Government shall:

#### use its best efforts to cause, at no financial cost to the Government,  that the Owner shall enter into the Land Acquisition Agreement and transfer the ownership of the Project Site to the Developer free and clear of all encumbrances, for the Project Site Price, as a condition precedent to the Financial Close in accordance with Article 3.2(c) and, if required to ensure a valid and binding transfer of the Project Site to the Developer, will procure the issuance of a Government resolution to that effect; and

#### grant, or use its best efforts to cause, at no financial cost to the Government, the grant to the Developer of all necessary rights of way and easements, and other rights (including any required to construct and maintain any Interface or any Gas, power, water (or any other utility) interconnections) required by the Developer in order to allow it to implement the Project. The Developer acknowledges that where obtaining certain rights of way and easements incurs a cost, the Developer is liable for such costs, to the extent such costs are reasonable and reflective of the going market rate for securing such rights and easements.

### The Government warrants that the Developer shall enjoy peaceful possession of the Project Site and that the Project Site:

#### is free and clear of all encumbrances and all activities that might interfere with the Developer implementing the Project, which have not been disclosed to, are not known or should not have been reasonably known by the Developer at the time of the signing of this Agreement; and

#### is in no way prohibited from being used for the Project, and all relevant Government Authorities have approved the Project Site to being used in such a way.

### The Developer shall use YTPP's 220 kV sub-station in consideration of the costs set out in Letter No. 704 from YTPP to Giovanni Rubini dated 2nd December 2016 (a copy of which is set out in Appendix 8).

## Delivery Point

### The Developer shall be permitted to, and the Government shall grant, or procure the grant of all necessary rights of way and easements required to, connect, remain connected to, and use, and evacuate electrical energy to the distribution network as required by the Developer to enable it to supply electricity to the delivery point  to be determined in accordance with the ToR (the "Delivery Point").

### The Government hereby acknowledges and agrees that the Developer shall only be responsible for the transmission of Net Electrical Energy up to the Delivery Point and shall not be responsible for transmission of Net Electrical Energy beyond such Delivery Point.

## Site Access

The Government shall use its best efforts to cause, at no financial cost to the Government, that sufficient access to and from the Project Site suitable for construction and operation of the Plant, subject to Applicable Laws, is made available so as to ensure that the Developer can properly carry out the Project.

ARTICLE 6

# Engineering Procurement and Construction of the Plant

## Construction

### The Developer shall by the Construction Start Date commence the construction of the Plant in accordance with the Project Schedule and shall complete the construction and commissioning of the Plant, in combined cycle mode, by the Scheduled Commercial Operation Date (as such date may be extended in accordance with the provisions of this Agreement).

### The Developer shall construct and complete the Plant in accordance with:

#### the Plant Design Documentation;

#### Good Industry Practice;

#### the Project Schedule;

#### all Applicable Laws and Applicable Permits;

#### the provisions of this Agreement;

#### the ToR; and

#### in a manner consistent with the requirements of the material damage, third party liability and business interruption insurance policies.

## Penalties for Delay

### The Developer acknowledges that the Government will suffer actual damages if, due to causes attributable to the Developer or any of its contractors and suppliers (other than the utility suppliers licensed and/or regulated by PSRC), the Developer fails to achieve the Commercial Operation Date on or before the COD Deadline. In the event of such a delay, the Developer shall pay penalties to the Government as provided below.

### Subject always to Article 6.2(a), if the Developer fails to achieve the Commercial Operation Date on or before the COD Deadline, the Developer shall pay, in addition to any penalties imposed by PSRC in accordance with all Applicable Laws, penalties at the rate of USD 3,750 per Day for each Day of delay from the COD Deadline until the earlier of:

#### the occurrence of the Commercial Operation Date of the Plant; and

#### the COD Longstop Date.

### Any such payments of penalties shall be made by the Developer to the Government within thirty (30) Days of the Developer's receipt of a notice from the Government which sets forth the amounts of penalties which are then due and payable, in accordance with Article 9.

### Notwithstanding Article 6.2(b), the Developer shall have the right to extend the COD Longstop Date for a period of 180 Days by paying a lump sum penalty of $3,000,000 and for the avoidance of doubt the Developer shall have no liability to pay penalties pursuant to Article 6.2(b) during such extended period, except for the penalties imposed by PSRC in accordance with all Applicable Laws.

## Commissioning Plan

### Within 90 Days after the Signing Date, the Developer shall elaborate and after the approval by the Independent Engineer submit to the Acceptance Commission a detailed plan delineating the actions to be undertaken by the Developer and/or the EPC Contractor towards commissioning of the Plant (the "Commissioning Plan"). The Acceptance Commission shall provide its comments and suggestions for modifications of such plan within thirty (30) Days of receipt of the same. The Developer shall within fifteen (15) Days revise the Commissioning Plan based on such comments and suggested modifications and re-submit the revised Commissioning Plan to the Acceptance Commission in accordance with the procedure set out in this Article. The final Commissioning Plan shall be approved by the Acceptance Commission, after taking into account all observations of the Government.

### The Commissioning Plan shall include as a minimum:

the scope and objectives of the Commissioning Tests, as required to be undertaken to prove that the Plant has been constructed and completed in compliance with Article 6.1 and is capable of commercial operation in combined cycle mode;

organisational and administrative responsibilities for undertaking the Commissioning Tests;

pre-conditions, conditions and logistical support requirements for undertaking the Commissioning Tests;

schedule for the detailed Commissioning Tests; and

the procedures and data collection, collation, analysis methodology and report documentation for the Commissioning Tests;

and shall comply with the requirements of all Applicable Laws.

ARTICLE 7

# StarT-UP, COmmissioning & COmmercial Operation

## Initial Energisation, Start-up Electricity and Water

### The Government shall use its best efforts to cause, at no financial cost to the Government, that, at the relevant Interface:

#### sufficient backfeed power as is required for the initial energisation and start-up, testing and commissioning of the Plant is provided to the Developer, pursuant to the Power Supply Agreement;

#### upon the provision of forty-five (45) Days' notice to the Government, the Transmission System is available for the initial synchronisation of the Plant's generators with the Transmission System; and

#### sufficient start-up Gas, electricity and water, and any other utilities as are required for the start-up, testing and commissioning of the Plant are made available, at the Developer's cost, pursuant to the relevant Project Agreement.

In each case, should the Government fail to use its best efforts to cause, at no financial cost to the Government, that the relevant utility or system is available as required for the start-up, testing and commissioning of the Plant, and such failure causes a delay in the achievement of the Commercial Operation Date, such failure will be classified as a breach by the Government of the terms of this Agreement for the purposes of Article 4.

## Commissioning Testing

### The Developer shall be responsible for the implementation of the Commissioning Tests in accordance with the Commissioning Plan and the Applicable Laws, and shall give the Acceptance Commission and the Independent Engineer 15 Days advance notice of all testing, as well as the requirements of each Commissioning Test in relation to the obligations of the Government pursuant to Article 7.1. Any such testing date shall be set by the mutual consent of the Developer and System Operator in accordance with Applicable Laws.

### A representative of the Acceptance Commission shall be entitled to be present at all Commissioning Tests.

### A representative of the Independent Engineer shall be present at and shall ascertain the results of all Commissioning Tests.

### During the Commissioning Tests, the Government shall use its best efforts to cause, best efforts to cause, at no financial cost to the Government, the Plant to be despatched to the extent reasonably required by the Developer in order to allow the Developer to carry out the Commissioning Tests as required, subject to the Transmission Code. Should the Government so fail to use its best efforts to cause, at no financial cost to the Government, the Plant to be despatched in accordance with the Commissioning Plan and as reasonably required by the Developer, and such failure causes a delay in the achievement of the Commercial Operation Date, such failure will be classified as a breach by the Government of the terms of this Agreement for the purposes of Article 4.

### A separate agreement shall be entered into between the Developer and the Offtaker in relation to the purchase of Net Electrical Energy during the Commissioning Period (the "Commissioning Electricity Purchase Agreement"). Such agreement shall be in the form of the Exemplary Documents approved by PSRC. During the Commissioning Period the Developer shall be entitled to receive payment for the Net Electrical Energy supplied to the Offtaker while performing Commissioning Tests in accordance with the lowest of (i) the Net Electrical Energy Tariff determined pursuant to the Tariff Schedule; or (ii) the highest tariff of any other generator in the relevant month.

## Acceptance Act

### Following the completion of the Commissioning Tests and the satisfaction by the Developer of other relevant requirements of the Applicable Laws, the Acceptance Commission shall promptly either:

#### issue an Acceptance Act confirming that it is satisfied that the Commissioning Tests and other relevant requirements have been satisfied; or

#### issue a notice saying that an Acceptance Act has not been issued, specifying any outstanding matters that must be attended to before the Acceptance Act can be issued.

### Where the Acceptance Commission has issued a notice pursuant to Article 7.3(a)(ii), the Developer shall attend to such matters and shall give the Acceptance Commission and the Independent Engineer further notice in accordance with Article 7.2(a) but dealing only with matters raised in the Acceptance Commission's notice and with a notice period of no less than four (4) working days for the purposes of Article 7.3(a) so that the procedures in in Article 7.3(a) are repeated as often as necessary to ensure that all outstanding matters are attended to and the Acceptance Act can be issued in accordance with 7.3(a)(i).

### The issue of an Acceptance Act shall indicate for the purpose of ascertaining the Commercial Operation Date that the Plant is complete, that the Commissioning Tests and other relevant requirements of the Applicable Laws have been satisfied and the Plant is capable of commercial operation in accordance with this Agreement, and as applicable the Power Purchase Agreement, following the Developer securing the Completion Act, and PSRC adopting a resolution on the License Revision and approval of the Tariffs.

## Commercial Operation

## From the Commercial Operation Date onwards the Developer shall operate, repair and maintain the Plant and provide Net Electrical Energy and make available Dispatchable Capacity to the Offtaker in accordance with:

### Good Industry Practice;

### the Applicable Permits;

### all Applicable Laws;

### the provisions of this Agreement; and

### the provisions of any relevant Project Agreement, particularly the Power Purchase Agreement.

ARTICLE 8

# Gas AND UTILITY SUPPLY

## Utility Interconnection Specifications

## The Developer shall ensure that the Plant Design Documentation contains all pertinent information and data regarding design, engineering materials, equipment, construction and other specifications which the Developer proposes to use to achieve tie-in to each Interface and to deliver each utility and service to the Plant, and shall coordinate with the relevant utility or service provider and the Government to ensure prompt and safe interconnection.

## Supply of Gas and Water

### The Government shall ensure that:

#### the Gas Supplier Facilities and water supplier facilities are constructed, tested and completed in sufficient time and with sufficient capacity, as set out in the Plant Design Documentation, so that Gas and water are capable of being delivered to the Gas Delivery Point and the water delivery Interface, at rates and on terms no less favourable to the Developer than those generally available to other similar commercial customers, in order that the Developer can test, commission the Plant in accordance with the Project Schedule and meet the Scheduled Commercial Operation Date and operate the Plant at the Dispatchable Capacity; and

#### from and after the Commercial Operation Date until the end of the Committed Offtake Term, the Developer is supplied at the Gas Delivery Point and the water supply Interface respectively all Gas and all water necessary for the Plant to make available the Dispatchable Capacity and generate Net Electrical Energy to the extent that the Plant is despatched by the Offtaker, in accordance with the Transmission Code.  The Developer agrees to provide the Gas Supplier and the Government with all pertinent information and data regarding design, engineering materials, equipment, construction and other specifications which the Developer proposes to use to achieve tie-in to the interconnection gas pipeline and to transmit Gas to the Plant, and shall coordinate with the Gas Supplier and the Government to ensure prompt and safe interconnection.

### Should the Developer be prevented from providing the Dispatchable Capacity when requested to do so by the System Operator and/or Offtaker, and receive full payment for the Contracted Capacity under the Power Purchase Agreement as a direct result of a Gas Supply Force Majeure the relevant provisions of Article 14.4 shall apply.

  - Non-conforming Gas

### The Developer shall have the right to reject all gas that does not meet the specifications of Gas and any disruption to its ability to provide Dispatchable Capacity and Net Electrical Energy caused by such rejection incompliance with the Gas specifications, to the extend the Developer is prevented from providing the Dispatchable Capacity when requested to do so by the System Operator and/or Offtaker, shall be classified as disruption of Gas supply for the purposes of determining the occurrence of a Gas Supply Force Majeure under this Agreement, subject to Article 10.3.

  - Risk of Loss of Gas

### The Developer shall not be responsible for and shall not bear the risk of damage to or loss of Gas prior to the delivery of such Gas to the Developer at the Gas Delivery Point. The Developer shall be responsible for and shall bear the risk of damage to or loss of Gas, for whatever reason, at all times from and after the delivery of such Gas at the Gas Delivery Point.

  - Gas and Electricity Counter Delivery Scheme

### The Government may request and the Developer shall, subject to the remainder of this Article 8.5, agree to enter into agreements with the Government or any party designated by the Government under which the Developer will be supplied with Gas (the value of which shall be calculated in accordance with the Gas tariff then in effect, including any adjustment relating to the condition of the Gas so supplied, which in any case shall comply with the standards set out in this Agreement) and will be obliged to deliver Net Electrical Energy (the value of which shall be calculated in accordance with the value attributed to the Net Electrical Energy in the Tariff Schedule). The Developer shall have the right to reasonably refuse the entry into or performance of or to terminate such agreements (in each case without any liability or adverse consequences for the Developer) if entry into or performance of such agreements:

### would result in breach of the Developer’s obligations under the Power Purchase Agreement;

### would put the Developer into a less favourable net (after-tax) economic position than if such agreements had not been entered into or performed by the Developer, as applicable, and the relevant Net Electrical Energy was supplied by the Developer to the Offtaker; or

### would be deemed as violation of any international sanctions.

## Supply of Utilities

### It shall be the responsibility of the Government to procure, at no financial cost to the Government, all facilities required to supply power and any other utilities, as envisaged by the Plant Design Documentation and requested by Developer in writing, in sufficient time and with sufficient capacity so that such utilities are capable of being delivered to the relevant Interface in order that the Developer can construct, test and commission and operate the Plant in accordance with the Project Schedule and meet the Scheduled Commercial Operation Date.

### It shall be the responsibility of the Government to use its best efforts to cause, at no financial cost to the Government, the supply of power and any other utilities, as envisaged by the Plant Design Documentation and requested by Developer in writing. in sufficient time and with sufficient capacity so that such utilities are capable of being delivered to the relevant Interface in order that the Developer operate the Plant at the Dispatchable Capacity.

ARTICLE 9

# PAYMENT STATEMENTS AND INVOICING

## Monthly Statement

### From the Effective Date onwards until the end of the Term, the Developer shall submit a monthly statement to the Government stated in Drams for any amounts owing to the Developer from the Government under this Agreement, including but not limited to:

#### any Assigned Amount;

#### any amount owing to the Developer in accordance with Article 15; and

#### any amount owing to the Developer in accordance with Article 10.1(b),

#### less any amounts the Developer may owe to the Government in accordance with Article 6.2, or any other provision of this Agreement, provided that the Developer shall not submit a monthly statement where the Developer is not owed any amounts from or to the Government for the relevant month.

### The monthly statement shall contain reasonably detailed calculations of the amounts payable under it, together with such further supporting documentation and information as the Parties may agree or as required by Applicable Laws.

## Invoicing, billing and payment

### If the monthly statement delivered in accordance with Article 9.1 shows that an amount is due from the Government to the Developer, the Developer shall, together with the delivery of the monthly statement, submit an invoice for that amount to the Government.

### If the monthly statement delivered in accordance with Article 9.1 shows that an amount is due from the Developer to the Government, then the Government may submit an invoice to the Developer for that amount.

### The relevant Party shall pay to the other Party the amount shown in the invoice as due on or before the date that is thirty (30) Days after the date the invoice was submitted to it.

### Any invoice delivered pursuant to this Article shall be paid in Drams.

### The payment of the net amount set out in the monthly statement shall be made without (and free and clear of any deduction for) set-off or counterclaim.

## Late Payments

## Late payment of any amounts due pursuant to this Agreement (other than penalties incurred pursuant to Article 6) shall bear interest at the Late Payment Rate.

## Disputed payments

### If at any time within thirty (30) Days from receipt by a Party of a monthly statement or invoice that Party disputes the monthly statement or invoice (in whole or in part) in good faith, that Party shall notify the other Party in writing of any disagreement with or exception to the calculation, including details of the monthly statement or invoice concerned, the amount in dispute and the basis for disputing the amount. In case a Party fails to dispute any invoice within the time period stated above, the amount of such invoice shall be deemed undisputed for the purposes of Articles 16.2(a) and 17.2(c).

### Where a Party disputes a payment pursuant to Article 9.4(a) the Parties shall confer within thirty (30) Days thereafter to resolve in good faith any such exceptions and disputes, in accordance with Article 18, if possible before the relevant due date of the disputed payment. If the attempt to resolve the dispute amicably and in good faith fails, the remained of Article 18 shall apply to any continuing dispute.

### Upon settlement or determination of the disputed amount, any amount agreed or determined to be owed to either Party shall be paid by the relevant Party within 30 Days, together with interest thereon at the Late Payment Rate. Such agreed or determined to be owed amounts shall be deemed undisputed for the purposes of Articles 16.2(a) and 17.2(c).

ARTICLE 10

# SALE AND PURCHASE OF ELECTRICITY AND CONTRACTED CAPACITY

## Sale and Purchase

### From the Commercial Operation Date onwards until the end of the Committed Offtake Term:

#### the Developer shall sell and the Government shall use its best efforts to cause, at no financial cost to the Government, the Offtaker to purchase from the Developer, the Net Electrical Energy despatched by the Offtaker pursuant to the Power Purchase Agreement; and

#### the Developer shall make available the Dispatchable Capacity, and the Government shall use its best efforts to cause, at no financial cost to the Government, the Offtaker to purchase from the Developer the Contracted Capacity pursuant to the Power Purchase Agreement.

### Tariff

#### The Government shall use its best efforts to cause, at no financial cost to the Government, the incorporation of the Tariff Schedule, without amendment, into the Licence, and shall procure that it is used to calculate the Tariffs to be paid by the Offtaker to the Developer as consideration for the Net Electrical Energy delivered to the Delivery Point and the Dispatchable Capacity made available under the Power Purchase Agreement, as described at Article 10.1 above.

#### Should the Tariff Schedule not be fully incorporated into the Licence and resulting, at any point during the Committed Offtake Period, in the Developer receiving from the Offtaker a lesser payment for Net Electrical Energy and/or Contracted Capacity than it would have otherwise received had the Tariff Schedule been fully incorporated, the Government shall pay to the Developer an amount equivalent to the difference between the amount actually paid by the Offtaker, and the amount that would have been payable to the Developer had the Tariff Schedule been fully incorporated into the Licence.

#### Such payments will be made directly to the Developer by the Government within 60 Days of the Government receiving written notification of the shortfall, and relevant statement and invoice in accordance with Articles 9.1 and 9.2.

### Offtaker Failure to pay the Tariffs

Should the Offtaker fail to pay any amount properly due and payable in accordance with the Power Purchase Agreement within 60 Days of the payment due date, then, upon notification by the Developer, the Developer shall assign to the Government, and the Government shall purchase, the Developer's right of claim against the Offtaker as such rights relate to the outstanding payment, for a price equivalent to ninety nine (99) per cent of the value of the outstanding principal payment (the "Assigned Amount").

## Inability to Achieve the Commercial Operation Date

### In the event the Developer shall be unable to achieve the Commercial Operation Date by a date that is on or after the Scheduled Commercial Operation Date directly as a result of (a) any action or failure to act without justifiable cause by the Government; or (b) due to any Adverse Condition Event, then the Plant shall be deemed to be providing Dispatchable Capacity equivalent to the Contracted Capacity adjusted for the Ambient Conditions, as confirmed by the Independent Engineer, and the Government shall compensate the Developer at a tariff equivalent to 0.0212USD per KWh for the period commencing on the date which is sixty (60) Days after the date on which the Commercial Operation Date would have been achieved, as assessed by the Independent Engineer, but for such action or failure to act on behalf of the Government or Adverse Condition Event; until the date on which the Commercial Operation Date has been achieved (the "Deemed Period") provided, however:

### that if upon completion of the Commissioning Tests, the Dispatchable Capacity demonstrated by the Commissioning Tests shall be less than the Contracted Capacity adjusted to take into account the Ambient Conditions (which shall include where the Developer is unable to achieve the Commissioning Tests), then the amounts paid by the Government during the Deemed Period in excess of the amounts that the Government would have had to pay if the Plant had been deemed to be providing the Dispatchable Capacity as so determined by the Commissioning Tests, shall be repaid by the Developer. If the Commissioning Tests are not completed due to the Developer’s fault by the Scheduled Commercial Operation Date, as extended pursuant to Article 4, then in addition to any other remedy provided for in this Agreement, repay to the Government for each Day of delay an amount equivalent to USD 0.0212 per KWh x 24 hours x the Contracted Capacity adjusted for the Ambient Conditions, as confirmed by the Independent Engineer;

### for each Day that compensation is due and payable to the Developer and actually paid by the Government, in accordance with this Article, the Committed Offtake Term shall reduce by one Day.

## Assignment of Claims

### If the Government is obliged to compensate the Developer under Articles 8.3, 10.2 and 14.4(b), the Developer shall assign to the Government any rights it has, if any, to claim damages against a Project Agreement counterparty or any other party in relation to the circumstances that has given rise to the Government's obligation to pay compensation to the Developer pursuant to provisions referred to above, and shall provide reasonable support to the Government if it seeks to claim such amounts from such Project Agreement counterparty or other part.

Article 11

# foreign exchange

## Foreign Exchange and Bank Accounts

The Parties hereby acknowledge and agree that, in accordance with all Applicable Laws, the Developer shall have the right to:

### open any foreign or local bank account in any currency; and

### freely convert any amount in Drams into any other currency and to transfer any such amount abroad.

ARTICLE 12

# Government Support

## In addition to any obligations identified elsewhere in this Agreement, the Government will provide the following support to the Developer, so that the Developer may successfully implement the Project.

### Approvals, Permits and Licences

The Government shall:

#### assist and facilitate the Developer to obtain all Applicable Permits as may be required by the Developer, provided that the Developer meets the requirements of all Applicable Laws, including the provision of the architectural-planning assignment, adoption of a resolution on conducting a special complex expert examination, appointment of the Expert Commission and the Acceptance Commission, approval of the Plant Design Documentation, granting of construction permits, the Acceptance Act, the Completion Act and the License, the License Revision, incorporation of the Tariff Schedule into the Licence, registration by PSRC of the Power Purchase Agreement, including by sending an official letter to PSRC supporting the granting of the License, the License Revision, registration of the Power Purchase Agreement, approval of Tariffs in accordance with the Tariff Schedule; and

#### from the Signing Date onwards, grant and maintain or cause to be granted and maintained those Applicable Permits or do such other thing required for the Project which only the Government or another Government Authority can grant or do, provided that the Developer has met the requirements of all Applicable Laws.

### Utilities, Access

The Government shall:

#### use its best efforts to cause, at no financial cost to the Government, the provision of access at the Interfaces determined in accordance with the ToR to suppliers of utilities (Gas in accordance with the GSA, water in accordance with the WSA, and electricity in accordance with the PSA), as are necessary for the Developer to construct, commission and operate the Plant (at the Dispatchable Capacity), at rates and on terms no less favourable to the Developer than those generally available to other similar commercial customers; and

#### use its best efforts to cause, at no financial cost to the Government, the provision of sufficient access at the boundary of the Project Site in accordance to the ToR to allow the Developer to evacuate power to the Delivery Point in accordance with Article 5.

### Investment and Tax Incentives

#### The Government shall use its best endeavours to ensure that all applicable investment and tax incentives available in Armenia in accordance with all Applicable Laws (including those that become available after the Effective Date), are granted by the applicable Government Authorities to the Developer, when duly requested by the Developer, and that all such incentives are valid for their maximum applicable period, provided the Developer meets the requirements of such Applicable Laws.

#### In particular, the Government shall use its best endeavours to ensure that the Developer is granted the fullest exemption or deferral possible, pursuant to all Applicable Laws, from any import tax, levy, customs duties for the goods imported for the Project, provided that the Developer has complied with all criteria necessary to benefit from the relevant incentives and exemptions.

### Import, Export

From the Signing Date onwards, upon the written request of the Developer, the Government shall use its reasonable endeavours to:

#### subject to the Developer complying with the requirements under all Applicable Laws, facilitate with formalities for importing into Armenia items of equipment and materials required for the Project;

#### subject to the Developer complying with all Applicable Laws, facilitate the formalities with Armenia Revenue Authority for the provision of services by the Armenia Revenue Authority that may be required for the success of the Project, including:

##### examining and valuating cargo;

##### facilitating electronic data interchange;

##### processing bills of entry and shipping; and

##### collecting customs duty.

## Project Finance

The Parties hereby acknowledge and agree that:

### the Government shall, reasonably co-operate and assist the Developer, without undertaking any obligations outside this Agreement, in obtaining financing for the Project;

### the Developer intends to develop and implement the Project on a project financed basis utilising debt from a variety of potential Financing Parties who may include national, international and multi-lateral lenders; and

### on that basis the Government agrees, and where relevant, shall use its best efforts to cause, at no financial cost to the Government, the agreement of the relevant counterparty to each Project Agreement that:

#### on receipt of the written consent of the Government, the Developer shall, subject to Applicable Laws, have the right to pledge or assign to the Financing Parties by way of security the benefit of its rights, title or interests in this Agreement, provided that such consent is not unreasonably delayed and can only be withheld by the Government should it reasonably believe that such a pledge or assignment is prejudicial to the national security of Armenia;

#### the Developer shall, subject to the terms of this Agreement, have the right to pledge or assign to the Financing Parties by way of security the benefit of its right title or interests in the Project Agreements and Preliminary Land Agreement; and

#### the Government (subject to having a right to object to the proposed direct agreement), will enter into a direct agreement with the Financing Parties in relation to the Project, reasonably in a form reflective of common practice in international project financed power projects similar to the Project, pursuant to which the Financing Parties will, amongst other rights, have the right to be notified of any impending termination of this Agreement, and as applicable, a Project Agreement, and allow the Financing Parties or a nominee the right to step in and remedy any default that has given rise to such termination, and/or nominate an approved substitute (in accordance with an approval process to be set out in the direct agreement (and including Government approval) to assume responsibility for the Developer's rights and obligations pursuant to this Agreement, or any Project Agreement, as applicable, subject to Applicable Law.

#### The Parties will act in good faith in negotiating any reasonable amendments required by the Financing Parties provided that any such amendments shall not increase the financial liabilities of the Government under this Agreement nor make the Government's obligations under this Agreement more onerous.

ARTICLE 13

# Indemnification and liability

## Limitation of Liability

Except as required by Article 13.2 of the Agreement, to the extent permissible under all Applicable Laws, neither Party shall be liable to the other Party in contract, tort, warranty, strict liability or any other legal theory for any loss of income, loss of opportunity, any indirect, consequential, incidental, punitive or exemplary damages. Neither Party shall have any liability to the other Party except pursuant to, or for breach of, this Agreement; provided, however, that this provision is not intended to constitute a waiver of any rights of one Party against the other with regard to matters unrelated to the Agreement, the Project Agreements or any activity not contemplated by the Agreement or Project Agreements or provided for under the Applicable Laws.

## Indemnification

### The Developer shall indemnify Government Authorities from and against all claims made against or suffered by Government Authorities, except to the extent such claims or any causes of action are found by an arbitral tribunal formed and having heard the dispute in accordance with Article 18 have resulted from such Indemnified Party’s gross negligence or wilful misconduct:

#### for any loss of or damage to property or death or injury to Persons resulting from any negligent act or negligent omission of the Developer in carrying out the Developer's obligations pursuant to this Agreement; and

#### under any Applicable Laws arising out of the Developer’s design, construction, testing, commissioning or operation of the Project.

### The Government shall indemnify the Developer and its Affiliates from and against all claims against or suffered by the Developer and/or its Affiliates for any loss of or damage to property or death or injury to Persons resulting from any negligent act or omission of any relevant Government Authority that arises out of or is connected with the performance of this Agreement and the Project Agreements.

### In the event injury or damage results from the joint or concurrent negligent or intentional acts or omissions of the Parties, each Party shall be liable under this indemnification in proportion to its relative degree of fault.

### The provisions of this Article 13.2 shall survive for a period of three (3) years following any termination of this Agreement.

## Indemnification for Fines and Penalties

### Any fines or other penalties incurred by a Party for non-compliance with any Applicable Laws shall not be reimbursed by the other Party but shall be the sole responsibility of the non-complying Party.

## Notice of Claims

Each Party (the "Indemnified Party") shall promptly notify the other Party (the "Indemnifying Party") of any Loss or proceeding in respect of which it is or may be entitled to indemnification under Article 13 of the Agreement including in relation to any claim made against the Indemnified Party by a third party (a "Third Party Claim"). Such notice shall be given as soon as reasonably practicable after the Indemnified Party becomes aware of the Loss or proceeding.

## Conduct of Claims

Subject to the rights of the insurers under any policy of insurance required pursuant to any of the Project Agreements the Indemnifying Party may at its own expense and with the assistance and co-operation of the Indemnified Party have control of the Third Party Claim including its settlement and the Indemnified Party shall not, unless the Indemnifying Party has failed to resolve the Third Party Claim within a reasonable period, take any action to settle or prosecute the Third Party Claim.

ARTICLE 14

# FORCE MAJEURE AND ADVERSE CONDITIONS

## Force Majeure or Adverse Condition Events

### A "Force Majeure or Adverse Condition Event" means the occurrence of any (or any combination of) events or circumstances, which (or any of the consequences of which) is not within the reasonable control, directly or indirectly, of the Party affected (the "Affected Party"), but only if and to the extent that:

#### such events or circumstances, despite the exercise of reasonable diligence and Good Industry Practice, cannot be prevented, avoided or removed by the Affected Party;

#### it prevents the Affected Party from performing its obligations under this Agreement, or if the Affected Party is the Developer, the Power Purchase Agreement, as the case may be, and the Affected Party has taken all reasonable precautions, due care and reasonable alternative measures in order to avoid the effect of such event on the Affected Party's ability to perform its obligations under this Agreement, or if the Affected Party is the Developer, the Power Purchase Agreement, as the case may be, and to mitigate the consequences thereof;

#### if the Affected Party is the Developer, if such circumstance occurs prior to the Commercial Operation Date, such event materially delays construction of the Plant, either

##### making it impossible for the Developer to satisfy the Project Schedule; or

##### requiring the Developer to incur material and substantial costs to satisfy the Project Schedule; and

#### the Affected Party has given the other Party (the "Non-Affected Party") notices in accordance with Articles 14.2(a) and 14.3.

### An "Adverse Condition Event" means:

#### Gas Supply Force Majeure;

#### Water Supply Force Majeure;

#### Utility Supply Force Majeure, other than in relation to the supply of Gas or water, taking place before the completion of the Commissioning Tests, (unless such Utility Supply Force Majeure is itself caused by a Force Majeure Event);

#### action or failure to act by a Government Authority (including the PSRC, the Expert Commission and Acceptance Commission), including any Government Permit (i) ceasing to remain in full force and effect not due to the fault or failure of the Developer or (ii) not being issued or renewed upon application having been properly made, provided the Developer has met the requirements of Applicable Laws;

#### failure of PSRC to adopt a resolution on the License Revision and the approval of the Tariffs based on the Tariff Schedule within [15] working days after the submission by the Developer to PSRC of the Completion Act and other documents required by the Applicable Laws, as well as fulfilment of all other relevant requirements of the Applicable Laws relating to the License Revision and approval of the Tariffs.; and

#### failure of the Offtaker to enter into a Power Purchase Agreement with the Developer at no fault of the Developer within [3] working days after the revision of the License by PSRC as set out in point (v) above.

### A "Force Majeure Event" means any Force Majeure or Adverse Condition Event which is an extraordinary event or circumstance of natural or man-made nature and which is not an Adverse Condition Event, including:

#### flood, earthquake;

#### epidemic or pandemic;

#### act or campaign of terrorism, or sabotage of a political nature;

#### nuclear, chemical or biological contamination or sonic boom;

#### acts of war (whether declared or not), invasion, armed conflict, act of foreign enemy or blockade occurring within or involving Armenia, which did not exist or could not have been reasonably foreseen at the time of signing this Agreement;

#### strikes, industrial action or lockouts (other than in each case caused by the Party seeking to rely on this clause, or Affiliates in the same group as that Party); and

#### Utility Supply Force Majeure caused by a Force Majeure Event.

### For the avoidance of doubt, a Force Majeure Event shall not include the following events:

#### lack of funds due to any reason;

#### any unexpected changes in the cost and quantities of plant or materials during the construction period;

#### collapse of buildings, fire, explosion or accident caused by a Force Majeure Event;

#### late delivery of machinery or other materials or a delay in the performance by any contractor or supplier (except where such late delivery or delay is itself attributable to a Force Majeure Event);

#### normal wear and tear or random flaws in materials and equipment or breakdown in equipment; or

#### hazards within the anticipated design criteria of the Project or which are otherwise unexceptional such that they can be reasonably anticipated, prevented or mitigated as part of Good Industry Practice.

#### any labour or trade dispute; or

#### collapse of buildings, fire, explosion or accident, other than those caused by a Force Majeure Event.

## Notification of Force Majeure or Adverse Condition Event by Affected Party

### To benefit from the protections afforded to the Affected Party during a Force Majeure or Adverse Condition Event under this Agreement, the Affected Party must notify the Non-Affected Party promptly of the events or circumstances (if known) constituting the Force Majeure or Adverse Condition Event (and in any case within ten (10) Days of becoming aware thereof), the likely duration of such events or circumstances and their consequences on its obligations or enjoyment of rights and benefits under this Agreement, or if the Affected Party is the Developer, the Power Purchase Agreement, as the case may be.

### After delivering a notice pursuant to Article 14.2(b), the Developer shall keep the Government informed of material developments relating to the relevant Force Majeure Event or Adverse Condition Event.

## Duty to mitigate a Force Majeure Event

### The Affected Party shall use all reasonable endeavours to continue to perform its obligations under the Agreement, or in relation to the Developer, the Power Purchase Agreement, as the case may be, and to mitigate or minimise the adverse effects of the Force Majeure or Adverse Condition Event.

### The Affected Party shall notify the Non-Affected Party of the steps it proposes to take to mitigate or minimise the effects of such Force Majeure or Adverse Condition Event, including any reasonable alternative means for performance of its obligations under the Agreement. The Non-Affected Party shall use reasonable endeavours to co-operate in taking such steps, to the extent that it is not prejudiced by doing so. The Affected Party shall also notify the Non-Affected Party of the nature and expected duration of the Force Majeure or Adverse Condition Event and continue to keep the Non-Affected Party informed until such time as it is able to perform its obligations.

### The Affected Party shall have the burden of proving that the circumstance, event or combination of circumstances or events constitutes a valid Force Majeure or Adverse Condition Event and that it has exercised reasonable diligence and efforts to avoid the effects of any alleged Force Majeure or Adverse Condition Event.

## Effect of Force Majeure or Adverse Condition Event

### Relief from Obligations

### Subject to Articles 14.2 and 14.3, to the extent the Affected Party is prevented, hindered or delayed in or from performing any of its obligations under this Agreement by a Force Majeure Event or Adverse Condition Event, the Affected Party shall not be in breach of this Agreement or otherwise liable for any such failure or delay in the performance of such obligations. The time for performance of such obligations shall be extended accordingly. The corresponding obligations of the other Party will be suspended, and its time for performance of such obligations extended, to the same extent as those of the Affected Party.

### Force Majeure or Adverse Condition Events after the Commercial Operation Date

#### Subject to Articles 14.2 and 14.3, if after the Commercial Operation Date Gas Supply Force Majeure or Water Supply Force Majeure affects the ability of the Developer to make available Dispatchable Capacity, then the Government shall use its best efforts to cause, at no financial cost to the Government, the Offtaker to continue making payments to the Developer, in relation to:

###### the Contracted Capacity, as if the Dispatchable Capacity was available; and

###### the Net Electrical Energy delivered to the Delivery Point,

#### in both cases in accordance with the Tariff Schedule, and shall it be impossible to cause the Offtaker to make the payments identified in this Article, the Government shall upon the Developer’s request compensate to the Developer the relevant amounts within 60 Days of the Government receiving such written request, subject to Article 10.3.

### Material Damage to the Plant

If a Force Majeure Event shall have occurred which results in material damage to or loss of the Plant, the following shall apply:

#### the Parties shall consult with one another as soon as practicable after the giving of a notice as provided in Article 14.2 concerning the effect of such Force Majeure Event upon the Milestone Dates, the Project Schedule, and/or the Commercial Operation Date, and the Milestone Dates and/or the Project Schedule, and/or the Scheduled Commercial Operation Date shall be equitably extended upon the agreement of both Parties to take into account such effect and the ability of the Developer or the EPC Contractor to reschedule Project activities to avoid or minimise overall delays resulting from the Force Majeure Event.

#### If the Parties are unable to agree upon the equitable adjustment of the Milestone Dates, and/or the Project Schedule, and/or the Scheduled Commercial Operation Date, within a period of sixty (60) Days after the giving of a notice as provided in Article 14.2, either Party shall be entitled to submit such dispute to the Independent Engineer for determination of the adjustment, if any, to the Milestone Dates, and/or the Project Schedule, and/or the Scheduled Commercial Operation Date.

### Term

The Parties agree that the Term, and the Government shall procure that the Committed Offtake Term, shall be extended by any period during which the Developer is prevented from performing its material obligations under this Agreement as a result of a Force Majeure Event.

### Exclusion of Payment Obligations from Force Majeure

Notwithstanding any other provision of the Agreement, neither Party shall be entitled to claim relief from its obligation to make a payment under the Agreement by reason of a Force Majeure Event.

Article 15

# change in law

## Consequences of a Change in Law

### If either Party believes that a Change in Law has occurred that will directly result in Costs or Savings, such Party shall promptly deliver to the other Party a notice identifying such Change in Law, and the net amount of Costs or Savings that have resulted from such Change in Law, or, as the case may be, other event or circumstance, subject in any event to the obligation of the Developer to minimise such Costs and to maximize such Savings in accordance with Good Industry Practice. Such Party may from time to time deliver to the other Party additional notices with respect to any such Change in Law, identifying additional Costs or Savings that have resulted or are reasonably expected to result from such Change in Law; provided that, any such additional notice shall be given not later than twelve (12) months after the Party giving such notice knew of or should have known of such additional Costs or realization of such additional Savings resulting from the occurrence of such Change in Law.

## Procedure for Claims

### Within seven (7) Days following the issuance or receipt of any notice specified in Article 15.1, as applicable, the Developer shall apply to PSRC for the revision of the Tariffs in accordance with the Tariff Schedule. Should PSRC fail to grant a Tariffs revision which would put the Developer into the same net (after-tax) economic position than if there were no Change in Law, then the following shall apply.

### The Parties shall, upon the written request of the Developer, meet at the offices of the Government within seven (7) days to discuss the subject matter. If within fourteen (14) Days after the commencement of such discussions, either Party disputes any of the contents of the notice, such dispute shall be submitted to the Independent Expert. The Parties shall use their best endeavours to cause Independent Expert to render his determination not later than forty-five (45) Days after being appointed.

### To the extent that a claim for Costs or Savings resulting from the occurrence of a Change in Law is not disputed or has been allowed by the Independent Expert, as if such Costs had not been incurred or such Savings had not been realized, the Developer shall include such amount so as to ensure that:

#### it is in the same net (after-tax) economic position; and

#### to be retroactive to the date upon which such Costs were incurred or such Savings were realized,

### within the monthly statement it submits to the Government in accordance with Article 9 and such amount shall be invoiced accordingly.

## Aggregation of Claims

### For purposes of this Article neither Party shall be entitled to assert any claim for Costs or Savings until such time as all claims of such Party under Article 15.2 exceed the equivalent of USD 100,000 in the aggregate, at which time all such claims of such Party may be asserted; provided, however, that when such claims have been asserted, the same rule shall apply in respect of future claims.

Article 16

# Events of Default

## Developer Events of Default

Each of the following events shall be a "Developer Event of Default":

### the Developer fails to make any payment owed by it to the Government under the Agreement within 90 (ninety) Days after it has become due and payable;

### the occurrence of an Insolvency Event relating to the Developer;

### termination of any of the Project Agreements as a result of the default of the Developer under those agreements;

### Abandonment of the Project;

### any representation made or warranty or covenant given by the Developer under the Agreement is found to be false or misleading;

### failure by the Developer or the Sponsor to comply with the terms of Sections 2.5 or 3.3(c); or

### unless as a result of a Force Majeure or Adverse Condition Event, or a breach of this Agreement by the Government the Developer fails to achieve the Commercial Operation Date by the COD Longstop Date unless and to the extent that the Developer elects to pay the lump sum penalty pursuant to Article 6.2(d) to extend the COD Longstop Date.

## Government Events of Default

Each of the following events shall be a "Government Event of Default":

### the Government fails to make any undisputed payment owed by it to the Developer under the Agreement within 180 (one hundred and eighty) Days after it has become due and payable;

### expropriation or compulsory acquisition by any Government Authority of the Project Site, the Plant or any material portion thereof that materially and adversely affects the operation of the Plant or any material asset of the Developer or any shares or other interest of a shareholder held in the Developer except where such compulsory seizure of assets is made for the purposes of collecting amounts owed by the Developer to the Government or Government Authority;

### the occurrence of an Insolvency Event relating to the Government.

Article 17

# Termination

## Termination for Non-Fulfilment of Conditions Precedent to the Effective Date

## Either Party may terminate this Agreement by giving written notice to the other Party if any condition precedent to the Effective Date has not been satisfied or waived by the relevant Parties by the Conditions Precedent Deadline, as such date may be extended in accordance with this Agreement, provided, however, that the Government shall be entitled to terminate this Agreement on the basis that only the conditions precedent relating to the Financial Close and/or the EPC Contract are not satisfied only in case such conditions precedent are not satisfied by the Financial Close Longstop Date. Upon the delivery of such notice of termination, this Agreement shall terminate on the date specified in such notice. Each Party hereby acknowledges and agrees that under such circumstances, it shall have no claim against the other for costs, damages, compensation or otherwise.

## Termination by the Developer and Consequences of Termination

### The Developer may terminate this Agreement in accordance with Article 17.4 in the following circumstances:

### if, the Developer fails to achieve Financial Close by the Financial Close Longstop Date, due to a breach by the Government of the terms of this Agreement. Each Party hereby acknowledges and agrees that following such termination, no Purchase Price shall be paid;

### if a Government Event of Default has occurred and is continuing for more than thirty (30) Days after being notified thereof in writing by the Developer. Each Party hereby acknowledges and agrees that following such termination, the Government will be obliged to purchase the Project Site and the Plant and pay the Developer the Government Event of Default Purchase Price;

### in case of any disruption in the supply of Gas at the Gas Delivery Point and/or disruption in the supply of water to the water Interface prevents the Developer from operating the Plant at its Dispatchable Capacity, except due to the fault of the Developer, cumulatively for more than 180 days during a calendar year, or the Government fails to make any undisputed payment to the Developer cumulatively for more than 180 days during a calendar year, each due to a Force Majeure Event or any other reason. Each Party hereby acknowledges and agrees that following such termination the Government will be obliged to purchase the Project Site and the Plant at the Government Event of Default Purchase Price;

## Termination by the Government and Consequences of Termination

The Government may terminate this Agreement in accordance with Article 17.4 in the following circumstances:

### if, the Developer fails to achieve Financial Close by the Financial Close Longstop Date, unless where such failure is due to a Force Majeure or Adverse Condition Event, or a breach by the Government of the terms of this Agreement. Each Party hereby acknowledges and agrees that following such termination, no Purchase Price shall be paid;

### if a Developer Event of Default is continuing for more than sixty (60) Days after being notified thereof in writing by the Government. Each Party hereby acknowledges and agrees that following such termination, the Government shall have the right, but not the obligation to purchase the Project Site and the Plant and pay the Developer the Developer Event of Default Purchase Price.

## Termination Procedure

### Unless otherwise specified in this Agreement, the Party entitled to terminate the Agreement shall do so by immediately issuing a notice in writing (a "Termination Notice") to the other Party and shall simultaneously deliver a copy of the Termination Notice to the Financing Parties.

### The Termination Notice shall specify a date which shall not be less than 90 (ninety) Days from the date of the Termination Notice on which the Agreement will terminate (the "Termination Period"). At the expiry of the Termination Period, and upon payment of the relevant Purchase Price, to the Developer by the Government, if applicable, the Agreement shall terminate without further notice. At such point the Developer shall terminate each and all of the Project Agreements.

### During a Termination Period, the Parties shall, continue to perform such of their respective obligations under the Agreement which are capable of being performed with the object, as far as possible, of ensuring continued availability of the Plant.

## Termination upon Expiry of the Term

### Unless terminated earlier, or extended, in both cases in accordance with the provisions of this Agreement this Agreement shall terminate on the last Day of the Term.

ARTICLE 18

# DISPUTE RESOLUTION

## Amicable Settlement

If any dispute or difference or claims of any kind arises between the Government and the Developer in connection with the construction, interpretation or application of any terms and conditions or any matter or thing in any way connected with or in connection with or arising out of the Agreement, or the rights, duties or liabilities of any Party under the Agreement, whether before or after the termination of the Agreement, then the Parties shall meet together promptly, at the request of any Party, in an effort to resolve such dispute, difference or claim by discussion between them.

## Assistance of the Independent Expert

## To the extent the Parties have not been able to resolve a dispute in accordance with Article 18.1 or a dispute is referred directly to this Article 18.2 such dispute shall be referred to an expert for a recommendation in accordance with the following provisions:

### the expert shall have demonstrated expertise in the area to which such dispute relates and shall not be an agent, employee, or contractor or a former agent, employee, or contractor of either Party.

### the Party initiating submission of the dispute to the expert shall provide the other Party with a notice stating that it is submitting the dispute to an expert and nominating the person it proposes to be the expert. The other Party shall, within thirty (30) Days of receiving such notice, notify the initiating Party whether such person is acceptable. If the Party receiving such notice fails to respond or notifies the initiating Party that the person is not acceptable, the Parties shall meet and discuss in good faith for a period of thirty (30) Days to agree upon a person to be the expert. If the Parties fail to meet or are unable to agree at the end of such thirty (30) Day period, either Party may request that the ICC International Centre for ADR nominates the expert, and such person so nominated shall be the expert for the purpose of resolving the dispute and the expert proceedings shall be carried out in accordance with Rules for the Administration of Expert Proceedings of the ICC.

### Consideration of the dispute by an Independent Expert shall be initiated by the Party seeking consideration of the dispute by the Independent Expert submitting within fifteen (15) Days of notification of the dispute to both the Independent Expert and the other Party written materials setting forth:

#### its description of the dispute in reasonable detail;

#### a statement of the initiating Party’s position; and

#### copies of records supporting the initiating Party’s position.

### Within fifteen (15) Days of the date that a Party has submitted the materials described in the preceding sentence, the other Party may submit to the Independent Expert and to the initiating Party:

#### its description of the dispute in reasonable detail;

#### a statement of the responding Party’s position; and

#### copies of any records supporting the responding Party’s position.

### Each Party shall designate one person knowledgeable about the issues in dispute who shall be available to the Independent Expert to answer questions and provide any additional information requested by the Independent Expert. Except for such person, a Party shall not be required to, but may, provide oral statements or presentations to the Independent Expert or make any particular individuals available to the Independent Expert.

### When consideration of the dispute by an Independent Expert is initiated, the Independent Expert shall be requested to provide a recommendation within twenty (20) Days after the expiry of the fifteen (15) Day response period provided above. If the Independent Expert’s recommendation is given within such twenty (20) Day period, or if the Independent Expert’s recommendation is given at a later time and no Party has at such time initiated any other proceeding concerning the dispute, the Parties shall review and discuss the recommendation with each other in good faith for a period of ten (10) Days following delivery of the recommendation before proceeding with any other actions.

### The costs of engaging an the Independent Expert shall be borne equally by the Parties, and each Party shall bear its own costs in preparing materials for, and making presentations to, the Independent Expert.

## Arbitration

### Failing settlement of a dispute by amicable settlement or with the assistance of an Independent Expert, the dispute shall be finally settled by binding arbitration.

### All disputes arising out of or in connection with the present contract shall be finally settled under the Rules of Arbitration of the International Chamber of Commerce (the "Rules") by three arbitrators appointed in accordance with the said Rules.

### The third arbitrator, who shall act as president of the arbitral tribunal, shall be jointly nominated by the other two arbitrators within 30 days of the confirmation of the second arbitrator. If the president of the arbitral tribunal is not nominated within this time period, the International Chamber of Commerce court shall appoint such arbitrator.

### The arbitration process shall be commenced by one Party issuing to the other a written notice, informing it of such commencement and appointing an Arbitrator. Upon receipt of the notice, the other Party shall appoint the second arbitrator. If a presiding arbitrator has not been chosen within 30 (thirty) Days of the date of notification of the arbitration, then the presiding arbitrator shall be chosen in accordance with the Rules.

### Place of Arbitration

The venue of arbitration shall be Geneva, Switzerland and the legal seat of arbitration shall be London, England.

### English Language

The language of the arbitration and all associated correspondence and documentation shall be English.

### Enforcement of Award

Any decision or award resulting from arbitration shall be final and binding upon the Parties. The Parties hereto agree that the arbitral award may be enforced against the Parties to the arbitration proceeding or their assets wherever they may be found and that a judgment upon the arbitral award may be entered in any court having jurisdiction thereof.

### Fees and Expenses

The fees and expenses of the arbitrators and all other expenses of the arbitration shall be initially borne and paid equally by the Parties subject to determination otherwise by the arbitrators. The arbitrators may provide in the arbitral award for the reimbursement to the successful Party of its reasonable costs and expenses in bringing or defending the arbitration claim, including reasonable legal fees and expenses incurred by that Party.

## Continued Performance

During any discussion, determination or arbitration pursuant to this Article 18 and pending any decision under it, the Parties shall continue to perform all of their obligations under the Agreement.

ARTICLE 19

# REPRESENTATIONS AND WARRANTIES

## Representations and Warranties of the Developer

The Developer represents and warrants to the Government that:

### it has full power and authority to execute, deliver and perform its obligations under the Agreement;

### it has taken all necessary action to authorise the execution, delivery and performance of the Agreement;

### the Agreement constitutes its legal, valid and binding obligation, enforceable against it in accordance with the terms hereof;

### there are no actions, suits or proceedings pending or to its best knowledge, threatened against or affecting it before any court, administrative body or arbitral tribunal which might materially and adversely affect its ability to meet or perform any of its obligations under the Agreement;

### it has complied with all laws applicable to it in all material respects which in the aggregate have or may have a material adverse effect on its ability to perform its obligations under the Agreement;

### no sums, in cash or in kind or inducement of any type, have been paid or will be paid by it or on its behalf, to any Person by way of fees, commission or otherwise for the granting of the Project or entering into the Agreement or for influencing or attempting to influence any officer or employee of any Government Authority in connection therewith;

## Representations and Warranties of the Government

The Government represents and warrants to the Developer that:

### it has full power and authority to execute, deliver and perform its obligations under the Agreement;

### it has taken all necessary action to authorise the execution, delivery and performance of the Agreement;

### the Agreement constitutes the legal, valid and binding obligation of the Government, enforceable against it in accordance with the terms hereof and are not subject to any further authorisation, budgetary approval or restriction or issuance of a separate budgetary guarantee;

### there are no actions, suits or proceedings pending or to its best knowledge, threatened against or affecting it before any court, administrative body or arbitral tribunal which might materially and adversely affect its ability to meet or perform any of its obligations under the Agreement;

### it has complied with Applicable Laws in all material respects which in the aggregate have or may have a material adverse effect on its ability to perform its obligations under the Agreement;

### no sums, in cash or in kind or inducement of any type, have been received or will be received, by it or on its behalf, from any Person by way of fees, commission or otherwise for the granting of the Project or entering into the Agreement or for influencing or attempting to influence any officer or employee of any Government Authority in connection therewith;

### it has complied, during the principal discussions with the Sponsor in respect of the Project, in awarding the Project to the Developer, the negotiation of this Agreement, and the Term with all Applicable Laws, including all relevant public procurement laws of Armenia;

### agrees that the execution, delivery and performance by it of the Agreement and all other agreements, contracts, documents and writings relating to the Agreement constitute private and commercial acts and not public or sovereign acts; and

### consents generally in respect of the enforcement of any judgment against it in any proceedings arising from disputes related to this Agreement and determined pursuant to Article 18 of this Agreement, it being expressly understood that this Article 19.2(i) does not apply to acts of the Government in its sovereign capacity in relation to the Developer or any other party in any jurisdiction to the giving of any relief or the issue of any process in connection with such proceedings.

ARTICLE 20

# MISCELLANEOUS PROVISIONs

## Notices

### Writing and delivery

Any notice or other communication in connection with the Agreement (each, a "Notice") shall be in writing, in English (or, if in another language, shall be accompanied by a translation into English certified by a representative of the notifying party, which translation shall be the governing version between the Parties) and delivered by hand, fax, email or courier using an internationally recognised courier company.

### Addresses

#### A Notice to the Developer shall be sent to the following address, or such other Person or address as the Developer may notify to the other Parties from time to time:

Name:		Armpower CJSC;

Address:	Vazgen Sargsyan Street Yerevan;

Email:		info@armpower.com;

Attention:	Mr Michele Arcangeletti;

#### A Notice to the Government shall be sent to the following address, or such other person or address as the Government may notify to the other Parties from time to time:

Name: [];

Address: [];

Email: [];

Attention: [];

### Deemed receipt

A Notice shall be effective upon receipt and shall be deemed to have been received at the time of delivery, if delivered by hand or courier.

## Assignment and Transfer

Except as otherwise provided in the Agreement and subject to any direct agreement (if relevant) or other relevant security agreement to be entered into in favour of any Financing Party (if relevant), the Developer shall not assign or transfer its rights, title, receivables or interest in the Agreement in favour of any Persons without prior written consent of the Government. In case of such transfer the obligations of the Developer should be transferred alongside the rights.

## Invalidity

### If any provision in the Agreement shall be held to be illegal, invalid or unenforceable, in whole or in part, the provision shall apply with whatever deletion or modification is necessary so that the provision is legal, valid and enforceable and gives effect to the commercial intention of the Parties.

### To the extent it is not possible to delete or modify the provision, in whole or in part, under Article 20.3(a) then such provision or part of it shall, to the extent that it is illegal, invalid or unenforceable, be deemed not to form part of the Agreement and the legality, validity and enforceability of the remainder of the Agreement shall, subject to any deletion or modification made under Article 20.3(a) not be affected.

### The Parties shall negotiate in good faith with a view to agreeing one or more provisions which may be substituted for any invalid, illegal or unenforceable provision and produce as nearly as is practicable in all the circumstances the appropriate balance of the commercial interests of the Parties.

## No partnership

Nothing in the Agreement shall be deemed to constitute a partnership between the Parties or constitute either Party the agent of the other Party for any purpose.

## Non-Solicitation

## From the Signing Date until the expiration of the Term of this Agreement, the Developer shall not, without the prior written consent of the Owner, solicit the employment of any employees that are currently employed by the Owner, or if such employees are subsequently terminated by the Owner, for a period of three years thereafter.

## Confidentiality

### General restriction

From the Signing Date until the date that is ten (10) years after the termination or expiry of this Agreement, and subject to the exceptions provided in Article 20.6(b) the Parties to the Agreement shall not, without the prior consent of the other Party, divulge or suffer or permit its officers, employees, agents or contractors to divulge to any Person (other than to any of its or their respective officers or employees who require the same to enable them properly to carry out their duties or to its or their respective banks or financiers) any of the contents of the Agreement or any commercially confidential information relating to the negotiations concerning the same which may come to a Party’s knowledge in the course of such negotiations concerning the operations, contracts, commercial or financial arrangements or affairs of the other Party.

### Exceptions

The restrictions imposed by Article 20.6(a) shall not apply to the disclosure of any information:

#### which now or hereafter comes into the public domain otherwise than as a result of a breach of the Agreement or the undertaking of confidentiality;

#### which is obtainable with no more than reasonable diligence from sources other than the Parties;

#### which is required by law or appropriate regulatory/constitutional authority to be disclosed to any Person who is authorised by law to receive the same;

#### which is in or comes into the possession of the receiving Party prior to the aforesaid publication or disclosure and which was or is not obtained under any obligation of confidentiality; and

#### which was or is obtained from a third party who is free to divulge the same and which was or is not obtained under any obligation of confidentiality.

### A Party may disclose the confidential information subject to obtaining confidential undertakings to keep the same confidential in terms not less strict than those imposed under the Agreement to:

#### a court, arbitral or administrative tribunal in the course of proceedings before the court, arbitral or tribunal to which the disclosing Party is a party;

#### Government Authorities;

#### any Financing Parties or to any consultants, banks, financiers, guarantors or advisers to the disclosing Party (including their respective managements and Boards of Directors);

#### any recognised exchange upon which the share capital of the Party or any Affiliate of the Party making the disclosure is proposed to be from time to time listed or dealt in; and

#### any insurers of either Party.

## Variation

No variation of the Agreement shall be effective unless in writing and signed by or on behalf of each Party and, to the extent its rights and obligations are concerned, the Sponsor.

## Waiver

### No failure or delay by any Party in exercising any right or remedy provided under the Agreement shall operate as a waiver of it, nor shall any single or partial exercise of any right or remedy preclude any other or further exercise of it or the exercise of any other right or remedy.

### Any waiver of a breach of the Agreement shall not constitute a waiver of any subsequent breach.

## Entire agreement

The Agreement contains the whole agreement between the Parties relating to the subject matter of the Agreement and to the exclusion of any terms implied by law which may be excluded by contract as at the Signing Date, and supersedes (in accordance with its terms) any other previous written or oral agreement or understanding between the Parties in relation to the subject matter of the Agreement.

## Survival

### Cancellation, expiration or earlier termination of the Agreement shall not relieve the Parties of obligations that by their nature should survive such cancellation, expiration or termination, including, without limitation, payment obligations, warranties, remedies, promises of indemnity and confidentiality.

## Sovereign Immunity

### The Parties unconditionally and irrevocably agree that the execution and performance of the Agreement constitute a private and commercial act.

### In addition, the Government unconditionally and irrevocably:

#### agrees that should any proceedings be brought against it or its assets in any jurisdiction in relation to the Agreement or any transaction contemplated by the Agreement, it will not claim immunity from such proceedings with respect to itself or its assets;

#### waives any right of immunity which it or any of its assets now has or may acquire in the future whether characterised as sovereign immunity or otherwise in any jurisdiction in connection with any such proceedings including, without limitation, immunity from service of process, immunity from jurisdiction or judgment of any court of tribunal and immunity from execution of a judgment; and

#### consents generally in respect of the enforcement of any judgment or arbitral award against it in any such proceedings in any jurisdiction to the giving of any relief or the issue of any process in connection with such proceedings (including the making, enforcement or execution against or in respect of any assets whatsoever irrespective of its use or intended use).

## Further assurance

Each Party shall, and shall use reasonable endeavours at no financial cost to procure that any necessary third party shall, from time to time, execute such documents and do such acts and things as the requesting Party may reasonably require for the purpose of giving the full benefit of the Agreement to the requesting Party.

## Counterparts

The Agreement may be entered into in any number of separate counterparts, all of which taken together shall constitute one and the same agreement. The Agreement shall be deemed concluded (entered into) between all of the Parties and the Sponsor upon exchange between all of the Parties and the Sponsor of the counterparts executed by all of the Parties and the Sponsor, upon which the Agreement shall enter into force, without prejudice to the Conditions Precedent.

## Governing law

The Agreement and any non-contractual obligations arising out of or in connection with it shall be governed by and construed in accordance with the laws of Armenia.

## Contract Language

This Agreement is executed in Armenian and English languages. The Parties acknowledge that the negotiations regarding this Agreement were held between the Parties in English, and agree that in case of any discrepancy between the Armenian and the English texts of this Agreement, the latter shall prevail.

IN WITNESS WHEREOF, the Parties and the Sponsor, intending to be legally bound, have caused the Agreement to be duly executed on the dates indicated next to their signatures below by their duly authorised representatives:

SIGNED by the GOVERNMENT OF THE REPUBLIC OF ARMENIA (acting on behalf of the REPUBLIC OF ARMENIA)

By						as its authorised representative

Signature:					Date:

Witnessed by

Signature: 					Date:

SIGNED by ARMPOWER CJSC

By						as its authorised representative

Signature: 					Date:

SIGNED by RENCO S.p.A

By						as its authorised representative

Signature: 					Date:

APPENDIX 1

Project Site

APPENDIX 2

Conditions Precedent

- Conditions Precedent under the Developer’s responsibility shall include:

true and complete and updated copies of the memorandum and articles of association of the Developer;

true and complete copies of resolutions adopted by the Developer’s board of directors authorising the execution, delivery and performance by the Developer of this Agreement and each of the other Project Agreements, certified by an authorised representative of the Developer;

true and complete copies of resolutions adopted by the Sponsor’s board of directors authorising the execution, delivery and performance by the Sponsor of this Agreement, certified by an authorised representative of the Sponsor;

true and complete copy of the shareholders’ agreement for the Developer;

true and complete copies of all Financing Documents executed by the Developer and the Financing Parties, where appropriate, certified by an authorised representative of the Developer;

a certificate from the Financing Parties in form and substance satisfactory to the Government confirming that all conditions to Financial Close have occurred;

true and complete copies of: (i) the organisational documents of the EPC Contractor; and (ii) the resolutions adopted by the EPC Contractor’s board of directors or shareholders authorising the execution, delivery and performance by the EPC Contractor of the EPC Contract, certified by an authorised representative of the EPC Contractor;

true and complete copies of: (i) the EPC Contract; and (ii) all guarantees and bonds provided by or on behalf of the EPC Contractor in accordance with the EPC Contract;

true and complete copies of: (i) the organisational documents of the O&M Contractor; and (ii) the resolutions adopted by the O&M Contractor’s board of directors or shareholders authorising the execution, delivery and performance by the O&M Contractor of the O&M Agreement, certified by an authorised representative of the O&M Contractor; and

a true and complete copy of the O&M Contract.

Conditions Precedent under the Government's responsibility shall include:

delivery of the Government Confirmation in respect of the Project;

true and complete copy of the Direct Agreement executed by the Government in relation to this Agreement;

the Licence;

the Land Acquisition Agreement executed by the Owner and the Developer; and

the Expert Commission and the Acceptance Commission appointed by the Government and, if applicable, regulations regulating the activities of such commissions approved.

A letter from the Ministry of Justice of the Republic of Armenia confirming that each of the counterparties to the Power Purchase Agreement, the Water Supply Agreement, the Gas Supply Agreement and the Power Supply Agreement are obliged under Applicable Laws to enter into their respective capacity with the Developer.

APPENDIX 3

Compensation on Termination

Government Event of Default Purchase Price

- A price, which is equal to the reasonable construction cost that will be documented by the Developer and in any case will be not less than 215.000.000 (two hundred fifteen million) USD, increased by the costs of connection to the Delivery Point, the Gas Delivery Point and connection points of other utilities (to be determined by an appropriate document), and the Project Site Price, total reduced in amount of 5% of the whole price for each full year of operation of the Plant by the Developer, the total further increased by 15% and (plus VAT when applicable), provided that the Plant meets the requirements set out in the ToR. Such price shall be paid by the Government within 12 months from the occurrence of events serving for the Developer as the legal ground for exercising its rights of requesting from the Government to purchase the Plant at this price.

- Developer Event of Default Purchase Price

If this Agreement is terminated following a Developer Event of Default, the Government shall have the right, but not the obligation, to purchase the Plant. If the Government exercises its option to purchase the Plant then it shall pay to the Developer a lump sum equivalent to:

- Senior Debt outstanding at the date of termination; PLUS

- Committed Equity; MINUS

- an amount equal to $5,375,000 as a penalty for the default of the Developer.

APPENDIX 4

Project Schedule

APPENDIX 5

Tariff Schedule

APPENDIX 6

Preliminary Land Agreement

APPENDIX 7

Terms of Reference

APPENDIX 8

YTPP Letter No. 704